## Sheet1
Name: RoBACHtic Symphony
Project: STEAM educational kit
Week Number
Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
System Design | ALL
PDR
Software Design |  |  | Christopher | Christopher | Christopher
Electrical Design |  |  | Christian | Christian | Christian
|  |  | Victor | Victor | Victor
Mechanical Design |  |  | Jeon | Jeon | Jeon
|  |  | Christian | Christian | Christian
Lesson Plan |  |  | Christopher | Christopher
CDR
Software Build | [5 empty] | Christopher | Christopher | Christopher
Electrical Build |  |  |  |  | Victor | Victor | Victor | Victor
[5 empty] | Christian | Christian | Christian | Christian
Mechanical Build |  |  |  |  | Jeon | Jeon | Jeon | Jeon
[5 empty] | Christian | Christian | Christian | Christian
Software Test | [7 empty] | Christopher
Electrical Test | [6 empty] | Victor | Victor
[7 empty] | Christian | Christian
Mechanical Test | [7 empty] | Jeon
Integration Phase 1: Software & Mechanical | [7 empty] | Jeon | Jeon
Integration Phase 1: Software & Electrical | [6 empty] | Christopher | Christopher | Christopher
Integration Phase 1: Electrical & Mechanical | [6 empty] | Christian | Christian
[7 empty] | Victor | Victor
Integration Phase 1 Testing | [7 empty] | ALL
Integration Phase 2: Software & System | [8 empty] | Christopher | Christopher
Integration Phase 2: Electrical & System | [7 empty] | Victor | Victor | Victor
[8 empty] | Christian | Christian | Christian
Integration Phase 2: Mechanical & System | [7 empty] | Jeon | Jeon | Jeon
[8 empty] | Christian | Christian | Christian
System Testing | [9 empty] | ALL
Final Inspection and Demonstration
Personnel:
Christian Santiago
Victor Alfaro
Christopher Semali
Sangeon Jeon
Instructions:
Step 1: | Add the milestones from the list below to the schedule. Do not add any additional milestones. PDR has been done for you.
Step 2: | Add the tasks from the list below to the schedule and specify the Task Leader from the Personnel list. Do not add any additional tasks. System Design has been done for you. Start from the end and add work backwards.
Note: | Each sub-system (software, electrical, and mechanical) must be scheduled for Design, Build, and Test. These sub-system names are placeholders until you determine your actual sub-systems.
Note: | After a sub-system is tested it needs integrated with another sub-system. Schedule time for integrating two sub-systems. NOTE: You must be done with one integration event before the next task can start using the same hardware.
Milestones
PDR
CDR
Tasks
System Design
Software Design
Software Build
Software Test
Electrical Design
Electrical Build
Electrical Test
Mechanical Design
Mechanical Build
Mechanical Test
Integration Phase 1: Software & Mechanical | Pick 1 Phase 1 Integration Event
Integration Phase 1: Software & Electrical
Integration Phase 1: Electrical & Mechanical
Integration Phase 1 Testing
Integration Phase 2: Software & System | Pick 1 Phase 2 Integration Event |  |  |  | <--- START HERE
Integration Phase 2: Electrical & System
Integration Phase 2: Mechanical & System